## Sheet1
Name | Date | Activity | Time | Category | Categories |  |  | Team Member Hours
Carter | 2016-04-22 | Senior Capstone Initial Meeting | 4 | M | Activity | Code | Hours | Name | Hours
Carter | 2016-04-25 | ECE End Semester Presentation | 1.5 | M | Meeting | M | 223.25 | Carter | 210.25
Carter | 2016-05-23 | Team Meeting | 1.5 | M | Python Controller | PC | 122.5 | Ben | 183
Carter | 2016-06-20 | Talked with ECE Engineers | 1 | M | Simulator Model | SM | 162.5 | Jeff | 181.25
Carter | 2016-08-16 | Read Chapters in Book | 4 | S | Robot Movement | RM | 63 | Trevor | 284
Carter | 2016-08-18 | Studied python | 3 | S | AI Algorithms | AA | 170 | Total Hours | 858.5
Carter | 2016-08-18 | Team Meeting with ECE Engineers | 1 | M | Summer | S | 74 | unclaimed | 0
Carter | 2016-08-23 | Team Meeting | 1.5 | M | Administrative | A | 43.25
Carter | 2016-08-26 | Dr. Kim Senior Capstone Lecture | 2 | M | Unclaimed | anything else | 0
Carter | 2016-08-26 | Team Meeting | 2 | M
Carter | 2016-08-27 | Draft of proposal and presentation | 4.5 | A
Carter | 2016-08-30 | Learning Python | 3 | S
Carter | 2016-08-30 | Team Meeting | 1.5 | M
Carter | 2016-09-01 | Updated Proposals | 0.5 | A
Carter | 2016-09-02 | Proposal Presentations | 3 | M
Carter | 2016-09-06 | Architecture Design | 1.25 | PC
Carter | 2016-09-06 | Team Meeting | 1 | M
Carter | 2016-09-06 | Finalized Proposal | 1 | A
Carter | 2016-09-09 | Meeting w/ Engineers | 0.5 | M
Carter | 2016-09-13 | Architecture Design | 3.5 | PC
Trevor | 2016-04-22 | Senior Capstone Initial Meeting | 4 | M
Trevor | 2016-04-25 | ECE End Semester Presentation | 1.5 | M
Trevor | 2016-05-23 | Team Meeting | 1.5 | M
Trevor | 2016-06-20 | Learn Python and Bluetooth research | 50 | S
Trevor | 2016-08-18 | Team Meeting with ECE Engineers | 1 | M
Trevor | 2016-08-23 | Team Meeting | 1.5 | M
Trevor | 2016-08-26 | Dr. Kim Senior Capstone Lecture | 2 | M
Trevor | 2016-08-26 | Team Meeting | 2 | M
Trevor | 2016-08-30 | Team Meeting | 1.5 | M
Trevor | 2016-08-30 | Serial port research | 3 | PC
Trevor | 2016-09-01 | Serial port programming | 3 | PC
Trevor | 2016-09-02 | Proposal Presentations | 3 | A
Trevor | 2016-09-04 | Serial Port communication | 2 | PC
Trevor | 2016-09-06 | Serial Port | 2 | PC
Trevor | 2016-09-06 | Serial Port | 1.25 | PC
Trevor | 2016-09-06 | Team Meeting | 1 | M
Trevor | 2016-09-08 | Installing Pyserial Library | 5 | PC
Trevor | 2016-09-13 | Python Serial Port working | 2 | PC
Jeff | 2016-04-22 | Senior Capstone Initial Meeting | 4 | M
Jeff | 2016-04-25 | ECE End Semester Presentation | 1.5 | M
Jeff | 2016-05-23 | Team Meeting | 1.5 | M
Jeff | 2016-08-18 | Studied Python | 5 | S
Jeff | 2016-08-18 | Read Chapters in Book | 3 | S
Jeff | 2016-08-18 | Team Meeting with ECE Engineers | 1 | M
Jeff | 2016-08-23 | Team Meeting | 1.5 | M
Jeff | 2016-08-26 | Dr. Kim Senior Capstone Lecture | 2 | M
Jeff | 2016-08-26 | Team Meeting | 2 | M
Jeff | 2016-08-29 | Looked over Docs | 0.25 | SM
Jeff | 2016-08-30 | Team Meeting | 1.5 | M
Jeff | 2016-08-31 | Simulator Work and Research | 0.5 | SM
Jeff | 2016-09-02 | Proposal Presentations | 3 | M
Jeff | 2016-09-03 | Socket comm. in sim. | 3.5 | SM
Jeff | 2016-09-06 | Socket comm. in sim. | 1.25 | SM
Jeff | 2016-09-06 | Team Meeting | 1 | M
Jeff | 2016-09-10 | WeBots sensor | 2.5 | SM
Jeff | 2016-09-12 | WeBots sensor | 1 | SM
Ben | 2016-04-22 | Senior Capstone Initial Meeting | 4 | M
Ben | 2016-04-25 | ECE End Semester Presentation | 1.5 | M
Ben | 2016-05-23 | Team Meeting | 1.5 | M
Ben | 2016-08-18 | Team Meeting with ECE Engineers | 1 | M
Ben | 2016-08-20 | Studied Python | 6 | S
Ben | 2016-08-23 | Team Meeting | 1.5 | M
Ben | 2016-08-26 | Dr. Kim Senior Capstone Lecture | 2 | M
Ben | 2016-08-26 | Team Meeting | 2 | M
Ben | 2016-08-26 | Looked over Docs | 0.25 | SM
Ben | 2016-08-29 | Worked with Simulator | 0.75 | SM
Ben | 2016-08-30 | Team Meeting | 1.5 | M
Ben | 2016-09-01 | Read Documentation on Simulator | 1 | SM
Ben | 2016-09-01 | Socket Programming | 1 | SM
Ben | 2016-09-02 | Proposal Presentations | 3 | M
Ben | 2016-09-05 | WeBots Reading | 1 | SM
Ben | 2016-09-06 | WeBots Reading / Programming | 3 | SM
Ben | 2016-09-06 | WeBots Reading / Programming | 1.25 | SM
Ben | 2016-09-06 | Team Meeting | 1 | M
Ben | 2016-09-11 | WeBots Sockets | 1.5 | SM
Ben | 2016-09-12 | WeBots Sockets | 0.5 | SM
Ben | 2016-09-13 | WeBots Sockets | 2 | SM
Carter | 2016-09-13 | Team Meeting | 1.5 | M
Ben | 2016-09-13 | Team Meeting | 1.5 | M
Trevor | 2016-09-13 | Team Meeting | 1.5 | M
Jeff | 2016-09-13 | Team Meeting | 1.5 | M
Jeff | 2016-09-13 | Architecture Design | 1 | SM
Jeff | 2016-09-16 | Simulator Modelling | 1.5 | SM
Carter | 2016-09-16 | Architecture Design | 1 | PC
Carter | 2016-09-19 | Architecture Design | 1 | PC
Jeff | 2016-09-19 | Simulator Modelling | 1 | SM
Jeff | 2016-09-20 | Simulator Modelling | 1 | SM
Ben | 2016-09-19 | Simulator Socket | 1 | SM
Ben | 2016-09-20 | Simulator Socket | 0.5 | SM
Carter | 2016-09-20 | Preliminary Report | 0.5 | A
Ben | 2016-09-20 | Team Meeting | 1.5 | M
Carter | 2016-09-20 | Team Meeting | 1.75 | M
Trevor | 2016-09-20 | Team Meeting | 1.75 | M
Jeff | 2016-09-20 | Team Meeting | 1.75 | M
Trevor | 2016-09-17 | Researching commercial robot options | 3 | RM
Jeff | 2016-09-22 | Simulator Modelling | 0.5 | SM
Jeff | 2016-09-23 | Simulator Modelling | 0.5 | SM
Carter | 2016-09-24 | Preliminary Report | 2 | A
Ben | 2016-09-25 | TPCIP/COM/Serial | 0.75 | SM
Jeff | 2016-09-26 | Simulator Modelling - SMORES | 0.5 | SM
Trevor | 2016-09-23 | Smores Meeting | 2 | RM
Ben | 2016-09-26 | TCPIP Programming | 1 | SM
Jeff | 2016-09-27 | Simulator Modelling - SMORES | 2.25 | SM
Carter | 2016-09-27 | Preliminary Report | 2.25 | A
Trevor | 2016-09-27 | Preliminary Report | 0.75 | A
Ben | 2016-09-27 | TCPIP Programming | 2.5 | SM
Carter | 2016-09-27 | Team Meeting | 1.5 | M
Ben | 2016-09-27 | Team Meeting | 1.5 | M
Trevor | 2016-09-27 | Team Meeting | 1.5 | M
Jeff | 2016-09-27 | Team Meeting | 1.5 | M
Jeff | 2016-09-28 | SMORES Modelling | 0.75 | SM
Carter | 2016-09-30 | Team Leader Meeting With Dr. Kim | 1.75 | M
Carter | 2016-09-30 | Preliminary Report | 0.75 | A
Jeff | 2016-10-01 | SMORES Modelling | 1.5 | SM
Ben | 2016-10-01 | TCPIP vCOM | 1 | SM
Carter | 2016-10-03 | Update Project Report | 1 | A
Jeff | 2016-10-03 | SMORES Modelling | 1 | SM
Ben | 2016-10-04 | COM Research | 2 | SM
Trevor | 2016-10-03 | Multithreading Implementation | 6 | PC
Trevor | 2016-10-03 | Research Multiprocessing | 2 | PC
Trevor | 2016-10-04 | Multiprocessing Implementation | 1 | PC
Carter | 2016-10-04 | Updated Project Report | 0.5 | A
Jeff | 2016-10-04 | SMORES Modelling | 1 | SM
Carter | 2016-10-04 | Team Meeting | 1.5 | M
Ben | 2016-10-04 | Team Meeting | 1.5 | M
Trevor | 2016-10-04 | Team Meeting | 1.5 | M
Jeff | 2016-10-04 | Team Meeting | 1.5 | M
Carter | 2016-10-11 | Design Arena | 2 | A
Jeff | 2016-10-12 | Play with Pixycam | 1 | RM
Ben | 2016-10-12 | COM Research | 1 | SM
Ben | 2016-10-13 | COM Research | 0.5 | SM
Carter | 2016-10-13 | Design Arena | 0.5 | A
Carter | 2016-10-13 | Team Meeting | 1.5 | M
Ben | 2016-10-13 | Team Meeting | 1.5 | M
Trevor | 2016-10-13 | Team Meeting | 1.5 | M
Jeff | 2016-10-13 | Team Meeting | 1.5 | M
Ben | 2016-10-16 | COM Research | 0.5 | SM
Ben | 2016-10-17 | COM Research | 2 | SM
Jeff | 2016-10-17 | Pixycam conn research | 1 | RM
Carter | 2016-10-18 | Design Arena | 1.25 | A
Carter | 2016-10-18 | Update Project Report | 0.5 | A
Carter | 2016-10-18 | Team Meeting | 1 | M
Ben | 2016-10-18 | Team Meeting | 1 | M
Trevor | 2016-10-18 | Team Meeting | 1 | M
Jeff | 2016-10-18 | Team Meeting | 1 | M
Trevor | 2016-10-16 | Serial Com Implementation | 3 | PC
Jeff | 2016-10-18 | Pixycam communication | 1 | RM
Ben | 2016-10-18 | COM Research | 0.5 | SM
Carter | 2016-10-22 | Building Arena | 5 | A
Ben | 2016-10-22 | COM Research | 0.5 | SM
Ben | 2016-10-23 | Com Research | 2 | SM
Ben | 2016-10-24 | COM Research | 1 | SM
Carter | 2016-10-25 | Update Diagrams | 1 | A
Jeff | 2016-10-24 | Pixy-to-Arduino Connection | 2 | RM
Jeff | 2016-10-25 | Pixy-to-Arduino Connection | 0.5 | RM
Carter | 2016-10-25 | Update Project Report | 1 | A
Ben | 2016-10-25 | Team Meeting | 2 | M
Ben | 2016-10-25 | COM Ports | 2 | SM
Trevor | 2016-10-25 | Team Meeting | 2 | M
Jeff | 2016-10-25 | Team Meeting | 2 | M
Carter | 2016-10-25 | Team Meeting | 2 | M
Carter | 2016-10-25 | Update Project Report and Presentation | 1.5 | A
Trevor | 10/22/1016 | Serial Com Implementation | 3 | PC
Carter | 2016-10-28 | Midterm Presentation | 2.5 | M
Ben | 2016-10-28 | Midterm Presentation | 2.5 | M
Trevor | 2016-10-28 | Midterm Presentation | 2.5 | M
Jeff | 2016-10-28 | Midterm Presentation | 2.5 | M
Ben | 2016-10-31 | TCPIP Implementation | 1.5 | SM
Jeff | 2016-10-31 | Pixy-to-Arduino Connection | 2 | RM
Jeff | 2016-11-01 | Pixy-to-Arduino Connection | 1.25 | RM
Carter | 2016-11-01 | Team Meeting | 1.5 | M
Jeff | 2016-11-01 | Team Meeting | 1.5 | M
Trevor | 2016-11-01 | Team Meeting | 1.5 | M
Ben | 2016-11-05 | TCPIP Implementation | 0.5 | SM
Ben | 2016-11-06 | TCPIP Implementation | 2.5 | SM
Carter | 2016-11-07 | Multiprocessing Research | 1 | PC
Ben | 2016-11-07 | TCPIP Implementation | 1.25 | SM
Carter | 2016-11-08 | Controller implementation | 2.5 | PC
Ben | 2016-11-08 | TCPIP Implementation | 1 | SM
Ben | 2016-11-08 | Team Meeting | 1.5 | M
Trevor | 2016-11-04 | Com-level refactoring | 6 | PC
Trevor | 2016-11-08 | Team Meeting | 1.5 | M
Trevor | 2016-11-04 | Smores Meeting | 4 | M
Carter | 2016-11-08 | Team Meeting | 1 | M
Jeff | 2016-11-08 | Team Meeting | 1 | M
Trevor | 2016-11-08 | Team Meeting | 1 | M
Ben | 2016-11-08 | Team Meeting | 1 | M
Jeff | 2016-11-10 | Arena Pictures/Pixie Cam Fix | 2.5 | RM
Carter | 2016-11-10 | Arena Pictures/Pixie Cam Fix | 2.5 | RM
Trevor | 2016-11-10 | Arena Pictures/Pixie Cam Fix | 1.75 | RM
Ben | 2016-11-12 | TCP Implementation | 2.5 | SM
Ben | 2016-11-13 | TCP Implementation | 1 | SM
Ben | 2016-11-14 | TCP Implementation | 1 | SM
Carter | 2016-11-14 | Controller implementation | 1.5 | PC
Carter | 2016-11-15 | Shopping list | 1.5 | A
Jeff | 2016-11-06 | Pixy-to-Arduino Connection | 3 | RM
Carter | 2016-11-15 | Team Meeting | 1 | M
Jeff | 2016-11-15 | Team Meeting | 1 | M
Trevor | 2016-11-15 | Team Meeting | 1 | M
Ben | 2016-11-15 | Team Meeting | 1 | M
Ben | 2016-11-15 | Simulator programming/troubleshooting | 1 | SM
Jeff | 2016-11-15 | Pixy-to-Arduino Connection | 3 | RM
Carter | 2016-11-17 | Update Project Plan | 0.5 | A
Carter | 2016-11-17 | Tinned Arena Wires | 0.5 | A
Carter | 2016-11-18 | Team Leader Meeting With Dr. Kim | 1 | M
Carter | 2016-11-21 | Queue API definition | 0.5 | PC
Jeff | 2016-11-21 | Pixycam testing | 1 | RM
Ben | 2016-11-21 | TCP TROUBLESHOOTING | 1 | SM
Ben | 2016-11-22 | SIMULATOR TROUBLESHOOTING | 5 | SM
Jeff | 2016-11-21 | Pixycam testing | 1.5 | RM
Ben | 2016-11-22 | Team Meeting | 2 | M
Carter | 2016-11-22 | Team Meeting | 1 | M
Jeff | 2016-11-22 | Team Meeting | 1 | M
Trevor | 2016-11-22 | Team Meeting | 1 | M
Ben | 2016-11-26 | Simulator TCP | 5.75 | SM
Carter | 2016-11-26 | Implement Communication Level | 9.75 | PC
Jeff | 2016-11-26 | Camera Calibration & Simulator Movement | 8.75 | SM
Trevor | 2016-11-26 | Implement Communication Level | 8.75 | PC
Ben | 2016-11-23 | TCPIP Simulator Troubleshooting | 1 | SM
Jeff | 2016-11-25 | Camera Calibration Research | 1.5 | RM
Trevor | 2016-11-22 | Com_Level | 3 | PC
Trevor | 2016-11-23 | Com_Level | 8 | PC
Trevor | 2016-11-25 | Com_Level | 6 | PC
Ben | 2016-11-25 | TCPIP Troubleshooting | 1 | SM
Carter | 2016-11-28 | TCP in Controller | 2 | SM
Carter | 2016-11-29 | Refactoring Controller | 6 | PC
Ben | 2016-11-29 | TCP to COM Layer | 1 | SM
Ben | 2016-11-29 | Team Meeting | 1.25 | M
Carter | 2016-11-29 | Team Meeting | 1.25 | M
Jeff | 2016-11-29 | Team Meeting | 1.25 | M
Trevor | 2016-11-29 | Team Meeting | 1.25 | M
Carter | 2016-12-03 | TCP Communication | 6.5 | SM
Ben | 2016-12-02 | TCP Communication | 3 | SM
Ben | 2016-12-03 | TCP Communication | 7 | SM
Carter | 2016-12-06 | Presentation & Report | 3.5 | A
Ben | 2016-12-06 | Team Meeting | 2 | M
Carter | 2016-12-06 | Team Meeting | 2 | M
Trevor | 2016-12-06 | Team Meeting | 2 | M
Jeff | 2016-12-06 | Team Meeting | 2 | M
Ben | 2016-12-07 | Presentation Practice | 1 | M
Carter | 2016-12-07 | Presentation Practice | 1 | M
Trevor | 2016-12-07 | Presentation Practice | 1 | M
Jeff | 2016-12-07 | Presentation Practice | 1 | M
Carter | 2016-12-07 | Preping Report | 2.5 | A
Ben | 2016-12-09 | Semester End Presentation | 2.5 | M
Carter | 2016-12-09 | Semester End Presentation | 2.5 | M
Trevor | 2016-12-09 | Semester End Presentation | 2.5 | M
Jeff | 2016-12-09 | Semester End Presentation | 2.5 | M
Jeff | 2016-12-12 | Simulator Multithreading | 1 | SM
Trevor | 2016-12-11 | Enhance Robot code | 3 | RM
Ben | 2016-12-09 | Team Meeting | 1 | M
Carter | 2016-12-09 | Team Meeting | 1 | M
Trevor | 2016-12-09 | Team Meeting | 1 | M
Jeff | 2016-12-09 | Team Meeting | 1 | M
Carter | 2016-12-24 | AI Research | 2 | AA
Carter | 2017-01-02 | AI Research | 3.5 | AA
Ben | 2017-01-04 | Team Meeting | 1.25 | M
Carter | 2017-01-04 | Team Meeting | 1.25 | M
Trevor | 2017-01-04 | Team Meeting | 1.25 | M
Jeff | 2017-01-04 | Team Meeting | 1.25 | M
Carter | 2017-01-07 | Localization Algorithm | 6.25 | AA
Trevor | 2017-01-07 | Localization Algorithm | 6.25 | AA
Trevor | 2016-12-28 | Break goals | 15 | RM
Trevor | 2017-01-09 | Ultrasonic | 2 | RM
Carter | 2017-01-04 | Team Meeting | 1.25 | M
Trevor | 2017-01-04 | Team Meeting | 1.25 | M
Jeff | 2017-01-04 | Team Meeting | 1.25 | M
Carter | 2017-01-13 | Meeting with Kim | 1 | M
Trevor | 2017-01-13 | Meeting with Kim | 1 | M
Jeff | 2017-01-13 | Meeting with Kim | 1 | M
Ben | 2017-01-13 | Meeting with Kim | 1 | M
Carter | 2017-01-13 | Localization Algorithm & TCP Multithreading | 7 | AA
Ben | 2017-01-13 | Multithreading of TCPController | 3.75 | SM
Ben | 2017-01-11 | Multithreading of TCPController | 1.5 | SM
Jeff | 2017-01-12 | Pixy-Aduino Communication | 1.5 | RM
Jeff | 2017-01-13 | Workdbuilding Testing | 5 | RM
Jeff | 2017-01-01 | AI Research | 5 | AA
Jeff | 2017-01-14 | Eyebot Simulator Modelling | 1 | SM
Carter | 2017-01-14 | Arduino Enhancements | 1 | RM
Jeff | 2017-01-18 | Eyebot Simulator Modelling | 0.5 | SM
Jeff | 2017-01-19 | Eyebot Simulator Modelling | 1 | SM
Jeff | 2017-01-20 | SMORES/Eyebot Webots API | 5.5 | SM
Carter | 2017-01-20 | Interprocess API update | 5 | PC
Carter | 2017-01-20 | Interprocess API update | 5 | PC
Ben | 2017-01-20 | TCP MultiThreading | 5 | SM
Jeff | 2017-01-22 | Simulator Arena Robot | 2 | SM
Jeff | 2017-01-23 | Team meeting | 1 | M
Trevor | 2017-01-23 | Team Meeting | 1 | M
Carter | 2017-01-23 | Team Meeting | 1 | M
Ben | 2017-01-23 | Team Meeting | 1 | M
Trevor | 2017-01-22 | Reverse engineering Camera image | 8 | AA | [5 empty] | /
Trevor | 2017-01-23 | Reverse engineering Camera image | 1.25 | AA
Jeff | 2017-01-27 | Multiple-pixy-to-arduino connections | 5.5 | AA
Carter | 2017-01-27 | TCP Communication | 7 | SM
Carter | 2017-01-28 | Readme Updates | 0.5 | A
Carter | 2017-01-29 | API documentation | 0.5 | A
Jeff | 2017-01-29 | Multiple-pixy-to-arduino connections | 1 | AA
Trevor | 2017-01-25 | Collect data for cameras | 4 | AA
Trevor | 2017-01-27 | Apply algorithm to data | 2 | AA
Trevor | 2017-01-29 | Research other algorithms for camera transformations | 2 | AA
Ben | 2017-01-27 | TCP Implementation | 7 | SM
Ben | 2017-01-30 | Team Meeting | 0.75 | M
Trevor | 2017-01-30 | Working on localization | 1 | AA
Trevor | 2017-01-30 | Team Meeting | 0.5 | M
Carter | 2017-01-30 | Team Meeting | 0.75 | M
Jeff | 2017-01-30 | Team Meeting | 0.75 | M
Carter | 2017-01-31 | API documentation | 0.25 | A
Jeff | 2017-01-31 | Multiple-pixy-to-arduino connections | 1 | AA
Carter | 2017-02-03 | Arduino API | 5 | RM
Jeff | 2017-02-03 | Multiple-pixy-to-arduino connections | 5 | AA
Jeff | 2017-02-06 | Multiple-pixy-to-arduino connections | 1 | AA
Ben | 2017-02-06 | Team Meeting | 1 | M
Carter | 2017-02-06 | Team Meeting | 1 | M
Trevor | 2017-02-06 | Team Meeting | 1 | M
Ben | 2017-02-03 | PDDL | 4.5 | AA
Jeff | 2017-02-08 | Multiple-pixy-to-arduino connections | 3 | AA
Trevor | 2017-02-08 | Multiple-pixy-to-arduino connections | 3 | AA
Carter | 2017-02-10 | Elegant shutdown | 5 | PC
Ben | 2017-02-10 | PDDL | 2 | AA
Ben | 2017-02-09 | PDDL | 1 | AA
Ben | 2017-02-12 | PDDL | 1 | AA
Jeff | 2017-02-10 | Sim API update, supervisor | 5 | SM
Trevor | 2017-02-10 | Programing Camera Simulator | 7.5 | AA
Trevor | 2017-02-12 | Programing Camera Simulator | 3 | AA
Trevor | 2017-02-13 | Programing Camera Simulator | 4 | AA
Trevor | 2017-02-13 | Team Meeting | 0.75 | M
Carter | 2017-02-13 | Team Meeting | 0.75 | M
Ben | 2017-02-13 | Team Meeting | 0.75 | M
Jeff | 2017-02-13 | Team Meeting | 0.75 | M
Jeff | 2017-02-14 | Simulator robot GPS | 0.5 | SM
Jeff | 2017-02-15 | Simulator robot compass | 0.5 | SM
Trevor | 2017-02-15 | Research with Camera Simulator | 5 | AA
Trevor | 2017-02-16 | Research with Camera Simulator | 3 | AA
Trevor | 2017-02-17 | Working on multiple cameras | 8.5 | AA
Carter | 2017-02-17 | Elegant shutdown | 1 | PC
Carter | 2017-02-17 | Meeting with Kim | 2 | M
Jeff | 2017-02-17 | Simulator robots API | 5 | SM
Jeff | 2017-02-20 | Smores API magnitude update | 0.5 | SM
Carter | 2017-02-20 | Controller Stateful Implementation | 1.5 | PC
Trevor | 2017-02-20 | Team Meeting | 0.5 | M
Carter | 2017-02-20 | Team Meeting | 0.5 | M
Ben | 2017-02-20 | Team Meeting | 0.5 | M
Jeff | 2017-02-20 | Team Meeting | 0.5 | M
Ben | 2017-02-17 | PDDL | 5 | AA
Ben | 2017-02-20 | PDDL | 3 | AA
Carter | 2017-02-24 | Updated python controller to use classes not globals | 5.5 | PC
Jeff | 2017-02-24 | Update smores API | 5 | SM
Trevor | 2017-02-24 | Localization | 7.75 | AA
Trevor | 2017-02-25 | Localization | 7 | AA
Trevor | 2017-02-27 | Team Meeting | 0.5 | M
Carter | 2017-02-27 | Team Meeting | 0.5 | M
Ben | 2017-02-27 | Team Meeting | 0.5 | M
Jeff | 2017-02-27 | Team Meeting | 0.5 | M
Ben | 2017-02-27 | TCP and PDDL | 5 | AA
Trevor | 2017-02-26 | Localization | 3 | AA
Ben | 2017-02-27 | PDDL | 1 | AA
Jeff | 2017-03-02 | Arena Camera | 2 | AA
Jeff | 2017-03-06 | Arena Camera | 2 | AA
Trevor | 2017-03-06 | Localization | 6 | AA
Ben | 2017-03-07 | Planning Alrithm | 2 | AA
Carter | 2017-03-10 | Controller refactoring | 6.5 | PC
Ben | 2017-03-08 | PDDL and Research | 2 | AA
Ben | 2017-03-10 | PDDL and Research | 5 | AA
Jeff | 2017-03-10 | Arena Camera | 5 | AA
Jeff | 2017-03-11 | Webots API | 4 | SM
Carter | 2017-03-11 | Midterm Presentation | 4 | A
Ben | 2017-03-11 | A* research and Implementation | 5 | AA
Ben | 2017-03-12 | A* research and Implementation | 2 | AA
Trevor | 2017-03-13 | Team Meeting | 0.5 | M
Carter | 2017-03-13 | Team Meeting | 0.5 | M
Jeff | 2017-03-13 | Team Meeting | 0.5 | M
Trevor | 2017-03-16 | Team Meeting | 1 | M
Carter | 2017-03-16 | Team Meeting | 1.25 | M
Ben | 2017-03-16 | Team Meeting | 1.25 | M
Jeff | 2017-03-16 | Team Meeting | 1.25 | M